Nutrition Services

Hunger and securing enough food to meet their nutritional needs is a struggle that many older adults and people with disabilities face in our region. This problem is only magnified for residents living in rural communities, people who are a racial minority, and those who have failing health or live alone. Food insecure older adults suffer a wide array of negative health outcomes including diabetes, depression, limitations in activities of daily living (ADLs), high blood pressure, congestive heart failure, heart attacks, gum disease, and asthma. OCWCOG is committed to improving food security for seniors and people with disabilities and manages programs to support this work internally as well as working with community partners who have the same focus.

PROGRAMS THAT SUPPORT FOOD SECURITY AT OCWCOG

Supplemental Nutrition Assistance Program (SNAP) – The SNAP program, formerly known as “food stamps”, is a Federal program that provides nutrition benefits to supplement the budget of needy families so they can purchase healthy food. OCWCOG eligibility workers process SNAP applications and determine and issue benefits. SNAP benefits are delivered monthly through electronic debit (EBT) cards.

Unfortunately, the SNAP participation rate for seniors is low. According to the National Council on Aging, three out of five seniors who qualify for SNAP do not participate. The factors that may contribute to low participation rates of seniors and people with disabilities may be the barriers they face related to mobility and technology. Misunderstanding about how the program works and who can qualify may also be an issue.

Food Box and Grocery delivery by the Senior Companion Program – The AmeriCorps Senior Companion Program (SCP), sponsored and operated by OCWCOG since 2018, uses National Service volunteers 55+ to help seniors 65+ age in place. A true gaps Program, SCP receives internal referrals from OCWCOG (e.g. Money Management, Meals on Wheels, Options Counselors) when a client is identified as needing 1-2 more hours of volunteer assistance each week. A chief component of the Program is taking the client grocery shopping; or, during the COVID-19 pandemic, either delivering groceries or food boxes to the client’s front door. Volunteers receive a tax-exempt stipend $3/hour, drive their own vehicles and are provided liability insurance, ongoing driver’s training, and are reimbursed .40/mile.

Meals on Wheels -- The Community Services Program (CSP), Meal on Wheels (MOW) program serves residents across Linn, Benton, and Lincoln Counties.  Our mission is to provide fresh, hot meals as well as a connection for local seniors and people with disabilities, supporting independent living at home.  Older adults age 60 and over, Native Americans/Alaskans age 55+, and people with disabilities can receive a hot meal delivered to their home or at a dining room location.

There are 11 meal site locations though out our region.  For mobile residents, meals are offered in a dining room setting providing an opportunity to reduce isolation and loneliness by connecting them with other community members.  During COVID restrictions, all dining rooms were suspended and take-out meals were provided to dining room participants.

Home-bound recipients can receive hot nutritious meals delivered to their doorstep by a MOW volunteer.  Delivery days vary depending on the meal site location.  To meet the needs of the diverse and rural population of Lincoln County with limited resources, hot meals are delivered Monday, Wednesday and Friday’s with frozen meals provided for Tuesday and Thursday’s.  Home delivered meals offer more than just a meal, each delivery serves as a well-check by a dedicated trained volunteer.  For some participants, this may be the only contact they have throughout a day.

CSP, MOW contracts with TRIO Community Health as a foodservice vendor.  Fresh and hot meals are planned by the vendor’s dietician then prepared at a central kitchen in Salem and delivered to each meal site location in our region.  Nutrition education articles are provided monthly with each menu and covers a variety of nutrition topics that relate to healthy nutrition for older adults.  Quarterly nutrition education seminars are also presented to our dining room recipients.  In addition, Older Americans Act (OAA) homebound MOW recipients receive nutrition education information during their initial and annual in-home reassessments.

Additional supports and services identified by trained staff and volunteers are referred to the Aging and Disability Resource Connection (ADRC) to ensure MOW recipients receive appropriate needed resources.

The MOW program pursues and receives fundraising and grant funds allowing our program to operate without a waitlist.

In March of 2020, Senior and Disability Services held a roundtable forum with community stakeholders to help identify gaps and barriers our communities experience around nutrition.

Utilizing Title III-C funding, MOW meal sites are located in the following locations:

Linn County Meal Site Locations			Service Schedule

Albany Senior Center					Monday – Friday @ 11:30 AM

Lebanon Senior Center					Monday – Friday @ 12:00 PM

Mill City First Presbyterian Church			Tuesday & Thursday @ 12:00 PM

Sweet Home Community Center				Monday, Tuesday, Friday @ 12:00 PM

Brownsville Christian Church				Tuesday & Thursday @ 12:00 PM

Benton County Meal Site Location			Service Schedule

Corvallis Elks Lodge					Monday – Friday @ 11:50 AM

Lincoln County Meal Sites				Service Schedule

Lincoln City Community Center				Monday, Wednesday, Friday @ 12:00 PM

Newport Senior Activity Center				Monday, Wednesday, Friday @ 12:00 PM

Siletz Tribal Community Center				Monday and Wednesday @ 12:00 PM

Toledo Trinity Methodist Church				Friday @ 12:00 PM

Waldport South County Community Center		Monday, Wednesday, Friday @ 12:00 PM

Goals and Objectives:  Nutrition Services

| Goal #1: Reduce Hunger and Food Insecurity for Seniors and People with Disabilities |  |  |  |
| --- | --- | --- | --- |
| MEASURABLE OBJECTIVES | KEY TASKS | LEAD POSITION & ENTITY | TIMEFRAME FOR 2021-2025 START DATE / END DATE |
| - Increase the Number of Older Adults Utilizing SNAP in our Region | - Partner with the OSU extension service who are also working on this issue | Eligibility and CSP Supervisors | Meet with OSU Extension by 9/30/2021 |
|  | - Develop a corps of senior volunteers for peer to peer outreach | Program Manager and CSP Supervisor | In place by 7/1/2022 |
|  | - Provide more hands- on assistance for older adults completing the application | Eligibility Supervisor and CSP Supervisor | Start 7/1/2021 |
|  | - Start completing monthly follow up phone calls with older adults who drop off of program during renewal process to see why they are not continuing | Program Managers ES Supervisor and CSP supervisor | Start by 10/1/2021 with quarterly assessment of the data |
|  | - Assess data quarterly to see if we can address barriers or if calls are helping |  |  |
| Goal #2: Improve the Sustainability of the Meals on Wheels Program |  |  |  |
| - Develop and Implement a Robust Volunteer Recruitment and Retention Strategy | - Commit 5% of CSP Program Manager time to volunteer recruitment and retention efforts | Program Director and Program Manager | Strategy Developed by 12/31/2021 and implemented 1/1/2022. Quarterly assessment of the gains starting 3/31/2022 |
|  | - Assess quarterly to see what is working, what isn’t, and where best to concentrate our efforts |  |  |
| - Annual assessment of MOW budget to look for cost savings and revenue earning opportunities | - Use the MOW Advisory Committee for this effort | MOW Supervisor and Program Director | Each year in December |
|  | - Implement action of suggestions provided |  |  |
| - Increase meals revenue by 5% through fundraising and grant writing | - Increase corporate sponsorships | Program Director Program Manager Council Members | Start work immediately and assess annually in March |
|  | - Track all efforts and Outcomes |  |  |
|  | - Distribute 4 direct mail distributions annually | Program Director and Program Managers | Four annually from November - October |
|  | - Create a Meals on Wheels Newsletter and distribute twice annually to donors, community partners, corporate sponsors, and local elected officials | Program Director and Program Managers | First in March 2022 Then September and March ongoing |
| Goal #3: Create Program Efficiencies by Collaborating with other Nutrition Providers |  |  |  |
| - Bring local stakeholders invested in food security to the table quarterly | - Assess places where we are duplicating efforts and work to reduce duplication | Program Director, Program Manager, and MOW supervisor | Start quarterly meetings September 2021 – assess impact August 2022 |
|  | - Identify ways we can leverage resources such as volunteers or delivery systems so resources spread further |  |  |
|  | - Create MOUs or systems for supporting each other in program delivery |  |  |
| ACCOMPLISHMENTS- UPDATES |  |  |  |